## Master
To use this spreadsheet, either highlight the entire document to copy/paste into Excel or use "File" --> "Make a copy" to create your own version of a Google spreadsheet. You can put your projected cart open date in the yellow field. The remaining fields will automatically adjust, but you'll want to review the dates to make sure they don't fall on weekends or holidays and to make sure they fit into your schedule. This was meant as just a guideline to get you started and has included every possible scenario. You can remove the items you're not going to do, such as videos or facebook ads or affiliates and adjust the timeline accordingly.
|  | Enter your date that your cart will open: |  | 2016-11-18
MARATHON | LAPS | TASKS BY LAPS | STATUS | DUE | WHO | STATS
PRELAUNCH ACTIVITIES - PROMOTION RELATED
1-Creation | Creative | Graphic - banners for webpages |  | 2016-09-23
1-Creation | Creative | Look & Feel - video on powerpoint template |  | 2016-09-23
1-Creation | Creative | Imagery - video emails - screenshots |  | 2016-09-23 |  |  | To improve click-thru rates
1-Creation | Content | Select sales funnel template in Leadpages for pre-launch videos |  | 2016-10-01
1-Creation | Content | Write content for landing page for the 4 videos |  | 2016-10-01
1-Creation | Content | Create the video content for Videos #1-#4 |  | 2016-10-01 |  |  | Each video should long enough to get the important messages across, but keep your audience in mind for their length threshoold.
1-Creation | Content | Create video content and layout for program sales page |  | 2016-10-01
1-Creation | Content | Determine upsell and downsell program, price and write sales page copy |  | 2016-10-03
1-Creation | Content | Create video for Video 1 - The Opportunity |  | 2016-10-10 |  |  | Focus on why they should listen to you and what problem of theirs you're going to solve
1-Creation | Content | Create video for Video 2 - How it Works & Education |  | 2016-10-10 |  |  | It's important that your prospects see that your solution is viable for them
1-Creation | Content | Create video for Video 3 - The Proof (Ownership experience) |  | 2016-10-10 |  |  | Focus on how your program has helped others
1-Creation | Content | Create video for Video 4 - The Offer (What You Get) |  | 2016-10-10 |  |  | Address objections and let them know how they can take action now
1-Creation | Admin | FB Ads - determine budget to run for two weeks - daily maximum or total budget. target audience |  | 2016-10-20 |  |  | Can have multiple ads running to promote videos 1-4
1-Creation | Creative | FB Ads - graphics for pre-launch videos 1-4 |  | 2016-10-21
1-Creation | Content | House List - Write content for emails 1-3 to Set the Stage |  | 2016-10-21 |  |  | You have the opportunity a few weeks before you launch to set the stage for what’s coming with your house list. Keep these emails informational and high content and let them on know that you have something cool to share with them shortly. These emails should have no links in them
1-Creation | Content | House List - Video 1 - Write emails 1-4 |  | 2016-10-17 |  |  | The goal of these emails is to pique their interest to get them to opt-in. The spirit of these email is that the videos are educational and beneficial to them. Drive them to your opt-in page.
1-Creation | Content | House List - Video 2 - Write emails 1-4 |  | 2016-10-17
1-Creation | Content | House List - Video 3 - Write emails 1-4 |  | 2016-10-17
1-Creation | Content | House List - Write email for Cart week - free content calls |  | 2016-10-17 |  |  | Continue to pique their interest to drive them to the cart week calls. Drive them directly to our cart week page, versus your opt-in page, as each of the cart week pages will have a "buy now" button on them. (Ask the Expert, Interviews, webcasts, additional training)
1-Creation | Content | Opt-in List - Write content for email - Opt-in confirmation/thank you page - Sent immediately |  | 2016-10-17
1-Creation | Content | Opt-in List - Write content for emails for Videos 1-4 |  | 2016-10-17 |  |  | Keep in mind that these are reminder messages. These people don’t necessarily realize they are getting access to a series of videos. The clearer you can be in your communication the less likely you’ll have spam complaints.
1-Creation | Content | Write social media posts (leave spaces for tracking links) |  | 2016-10-17
2-Offering | Technical | Set up tracking links for Social media posts and email to each of these pages - Video 1-4, sales page |  | 2016-10-23
2-Offering | Technical | Set up the order form for pre-launch videos 1-4 |  | 2016-10-23 |  |  | Track how many people order from for each video
3-Delivery | Content | Use leadpages to create sales funnel page for prelaunch videos 1-4 |  | 2016-10-17
2-Offering | Technical | Opt-in List - Set up content for email - Opt-in confirmation/thank you page - Sent immediately |  | 2016-10-22
2-Offering | Technical | Opt-in List - Set up content for emails for Videos 1-4 |  | 2016-10-22
2-Offering | Technical | House List - Set up content for emails 1-3 to Set the Stage |  | 2016-10-22
2-Offering | Technical | House List - Video 1 - Set up emails 1-4 |  | 2016-10-22
2-Offering | Technical | House List - Video 2 - Set up emails 1-4 |  | 2016-10-22
2-Offering | Technical | House List - Video 3 - Set up emails 1-4 |  | 2016-10-22
2-Offering | Technical | House List - Set up email for Cart week - free content calls |  | 2016-10-22
2-Offering | Technical | Downsell List - Set up emails offering downsell program/product |  | 2016-10-22
2-Offering | Technical | Upsell List - Set up emails offering upsell program/product |  | 2016-10-22
3-Delivery | Admin | Schedule social media posts with tracking links |  | 2016-10-27
| Admin | Set up FB Ads |  | 2016-10-28
3-Delivery | Admin | FB Ads running through Close Cart date |  | 2016-11-11
AFFILIATES
1-Creation | Admin | Determine commission percentages, banners and affiliate email copy, social media |  | 2016-10-03 |  |  | How many items to offer affiliates
1-Creation | Admin | Affiliate Assets - write affiliate email copy, social media posts |  | 2016-10-10
1-Creation | Content | All Affiliates - Write Save the Date Emails 1-2 |  | 2016-09-19
1-Creation | Content | Interested Affiliates - Write email to Keep them Engaged #1 - Details of the 4 videos |  | 2016-10-14 |  |  | Here’s your game plan with details about the launch with dates and commissions and prizes. Let them know swipe copy will be coming soon
1-Creation | Content | Interested Affiliates - Write email to Keep them Engaged #2 - Details of the 4 videos |  | 2016-10-14 |  |  | Provide them with details of the 4 videos – just a simple summary. Reminde them when they'll receive their swipe copy (which they should plan to personalize)
1-Creation | Content | Interested Affiliates - Video 1 - Create content for emails 1-2 |  | 2016-10-14 |  |  | Provide their personalized affiliate link in the body of your email. Provide swipe copy for the first video with their personalized link embedded in the copy. Provide details of how to gain access to the Affiliate Resource Center. Give them directions on how to use swipe copy correctly. Remind them to use the link shortening tools such as bit.ly or tinyurl. Your main message is in your voice but their swipe copy is in the voice of their affiliate mailing to their list.
1-Creation | Content | Interested Affiliates - Video 2 - Write content for emails 1-2 |  | 2016-10-14 |  |  | Let them know how the launch is going and how the precious videos were received. Provide their personalized aff link in the body of email. Provide swipe copy for the 2nd thru 4th video wit their personalized link embedded in the copy. Provide details to their Affiliate Resource Center to access their commission detials. Give them directions on how to use swipe copy correctly. Remind them to use the link shortening tools such as bit.ly or tinyurl.
1-Creation | Content | Interested Affiliates - Video 3 - Write content for emails 1-2 |  | 2016-10-14
1-Creation | Content | Interested Affiliates - Video 4 - Write content for email 1 |  | 2016-10-14
1-Creation | Content | Interested Affiliates - Cart Open - Write email content |  | 2016-10-14 |  |  | Share that you're offering early bird pricing (if you are) an appropriate cart close deadlines. Same as above
1-Creation | Content | Interested Affiliates - Cart Week - Write valuable content offerings |  | 2016-10-14 |  |  | Over the course of the days that your cart's open, you'll want to continually have great content offerings so your affiliates have a reason to mail their lists. Ideally, you'll have a few different emails to send during this time based on your offerings. Same as above
1-Creation | Content | Interested Affiliates - Cart Close - Write email content |  | 2016-10-14 |  |  | Remind them of cart close date. Same as above
1-Creation | Creative | Create banners for affiliates |  | 2016-10-14
2-Offering | Technical | Set up commission percentages, banners and affiliate email copy, social media |  | 2016-10-10
2-Offering | Technical | All Affiliates - Set up Save the Date Emails 1-2 |  | 2016-09-19 |  |  | Set up and send right away
2-Offering | Technical | Interested Affiliates - Set up email to Keep them Engaged #1 - Details of the 4 videos |  | 2016-10-17
2-Offering | Technical | Interested Affiliates - Set up email to Keep them Engaged #2 - Details of the 4 videos |  | 2016-10-17
2-Offering | Technical | Interested Affiliates - Video 1 - Set up content for emails 1-2 |  | 2016-10-17
2-Offering | Technical | Interested Affiliates - Video 2 - Set up content for emails 1-2 |  | 2016-10-17
2-Offering | Technical | Interested Affiliates - Video 3 - Set up content for emails 1-2 |  | 2016-10-17
2-Offering | Technical | Interested Affiliates - Video 4 - Set up content for email 1 |  | 2016-10-17
2-Offering | Technical | Interested Affiliates - Cart Open - Set up email content |  | 2016-10-17
2-Offering | Technical | Interested Affiliates - Cart Week - Set up valuable content offerings |  | 2016-10-17
2-Offering | Technical | Interested Affiliates - Cart Close - Set up email content |  | 2016-10-17
LAUNCH ACTIVITIES - PROGRAM RELATED
1-Creation | Creative | Create banner for sales page |  | 2016-09-24
1-Creation | Content | Determine set up of program - Fast Forward and Weekly Drip - dashboard |  | 2016-09-24 |  |  | October 1 - all video content done
2-Offering | Content | Determine upsell and downsell program, price and write sales page copy |  | 2016-09-29
2-Offering | Admin | Determine guarantee, return policy, full pay and multi-pay |  | 2016-09-24
1-Creation | Content | Determine free content |  | 2016-09-24 |  |  | Determine what free content you'll be offering during your cart open week
1-Creation | Content | Write copy for your sales/cart open page |  | 2016-09-29
1-Creation | Content | Write copy for thank you page |  | 2016-09-29
2-Offering | Content | Opt-in List - Write email content for Charter membership |  | 2016-10-17
2-Offering | Content | Opt-in List - Cart Opens - Write email content for Fast Action Bonus -example: Free Trial / Bonuses/ 30min call - $997 |  | 2016-10-17
2-Offering | Content | Opt-in List - Cart Week - Write email content for valuable content offerings |  | 2016-10-17 |  |  | Keep them engaged with valuable content provided during cart open week. Provide correct URLs for all offerings. Remind them throughout the week of the cart close date.
2-Offering | Content | Opt-in List - Write Email when Cart Closes |  | 2016-10-17 |  |  | Remind them it’s decision time and the value of what they’ll get with your product, including bonuses. Link to your cart close page. Provide a link for them to ask you questions before purchasing
1-Creation | Content | Downsell List - Write emails offering downsell program/product |  | 2016-10-17
1-Creation | Content | Upsell List - Write emails offering upsell program/product |  | 2016-10-17
2-Offering | Content | Customer List - Write email content for Pay campaign |  | 2016-10-17
2-Offering | Content | Customer List - Write email content for Stay campaign to include stick strategies |  | 2016-10-17
2-Offering | Content | Customer List - Write reminder email the day before |  | 2016-10-17
2-Offering | Content | Customer List - Write reminder email the morning of |  | 2016-10-17
2-Offering | Content | Opt-in List - Write Email when Cart Closes |  | 2016-10-17
3-Delivery | Technical | Customer List - set up email content for Fast Forward to include course content and stick strategies |  | 2016-10-22
3-Delivery | Technical | Customer List - set up email content for Weekly program - Emails 1-10 to include course content and stick strategies |  | 2016-10-22
2-Offering | Technical | Set up video opt-in form |  | 2016-10-22
2-Offering | Technical | Set up main product order form with appropriate tags |  | 2016-10-22
2-Offering | Technical | Set up an upsell/downsell buy buttons |  | 2016-10-22
2-Offering | Technical | Set up opt-in form for cart close page |  | 2016-10-22 |  |  | For when product is offered again
1-Creation | Content | House List - Set up email content for cart week free content calls |  | 2016-10-22
3-Delivery | Technical | Opt-in List - Set up email content for Charter membership |  | 2016-10-22
3-Delivery | Technical | Opt-in List - Cart Opens - Fast Action Bonus - example: Free Trial / Bonuses/ 30min call - $997 |  | 2016-10-22
3-Delivery | Technical | Opt-in List - Cart Week - Set up email content for valuable content offerings |  | 2016-10-22
3-Delivery | Technical | Opt-in List - Set up email when Cart Closes |  | 2016-10-22
3-Delivery | Content | Opt In List (minus Customers) and people who went through the 7-day trial and didn't purchase - send people to downsell campaign |  | 2016-10-22
3-Delivery | Technical | Downsell List - Set up emails offering downsell program/product |  | 2016-10-22
3-Delivery | Technical | Upsell List - Set up emails offering upsell program/product |  | 2016-10-22
3-Delivery | Technical | Customer List - Set up reminder email the day before |  | 2016-10-22
3-Delivery | Technical | Customer List - Set up reminder email the morning of |  | 2016-10-22
3-Delivery | Technical | Customer List - set up content for Pay campaign |  | 2016-10-22
3-Delivery | Technical | Customer List - set up email content for Fast Forward to include course content and stick strategies |  | 2016-10-22
3-Delivery | Technical | Customer List - set up email content for Weekly program - Emails 1-10 to include course content and stick strategies |  | 2016-10-22
2-Offering | Admin | Confirm that merchant services company is prepared for additional sales volume |  | 2016-10-03
2-Offering | Admin | Potentially have a back up of merchant account |  | 2016-10-03
3-Delivery | Technical | Set up sales page and countdown timer |  | 2016-10-14
3-Delivery | Technical | Set up Thank you page |  | 2016-10-14
3-Delivery | Technical | Set up Cart Close page |  | 2016-10-14 |  |  | This will replace the sales page tell people that the program is no longer being offered.
3-Delivery | Technical | Install memberium on development site |  | 2016-09-30
3-Delivery | Technical | Start adding course content |  | 2016-10-01
3-Delivery | Technical | Complete set up of programs - one for Fast Forward and Weekly content |  | 2016-10-21 |  |  | Start 10/6 - 10/14
3-Delivery | Technical | Set up downsell/upsell pages |  | 2016-10-28
3-Delivery | Technical | Testing starts - webpages and emails |  | 2016-10-29 |  |  | Start testing through purchase and access to membership site for Fast Forward and Weekly plan
3-Delivery | Technical | Testing ends |  | 2016-11-12 |  |  | Everything fully tested
3-Delivery | Content | House List, Social Media, FB Ads - Video #1 Live - Charter membership starts |  | 2016-11-11 |  |  | Start of Pre-Launch - Charter Membership $99/week or $797 and ends on 11/4
3-Delivery | Content | House List, Social Media, FB Ads - Video #2 Live |  | 2016-11-13 |  |  | Check stats
3-Delivery | Content | House List, Social Media, FB Ads - Video #3 Live |  | 2016-11-17 |  |  | Check stats
3-Delivery | Content | House List, Social Media, FB Ads - Video #4 Live |  | 2016-11-19 |  |  | Check stats
3-Delivery | Content | Opt-in List - Cart Opens - Fast Action Bonus - Free Trial / Bonuses/ 30min call - $997 |  | 2016-11-20 |  |  | Start of Launch - first 30 people get the call - $119 or $997
3-Delivery | Content | Opt-in List - Cart Week - valuable content offerings |  | 2016-11-25 |  |  | Check stats
3-Delivery | Content | Opt-In List - Cart Closes - Send email |  | 2016-11-30 |  |  | Check stats
3-Delivery | Content | Customer List - Reminder email the day before |  | 2016-11-30 |  |  | Check stats
3-Delivery | Content | Customer List - Reminder email the morning of |  | 2016-12-01
|  | Program opens |  | 2016-12-01
AFFILIATES
3-Delivery | Content | Interested Affiliates - Send reminder email promoting Video #1 |  | 2016-11-09
3-Delivery | Content | Interested Affiliates - Send reminder email promoting Video #2 |  | 2016-11-11
3-Delivery | Content | Interested Affiliates - Send reminder email promoting Video #3 |  | 2016-11-15
3-Delivery | Content | Interested Affiliates - Cart Open - Send email |  | 2016-11-18
3-Delivery | Content | Interested Affiliates - Cart Week - Send email valuable content offerings |  | 2016-11-22
3-Delivery | Content | Interested Affiliates - Cart Closes - Send email and Class #1 Starts on 11/17 |  | 2016-11-29
POST LAUNCH ACTIVITIES
3-Delivery | Content | Customer List - Set up email content for Emails 3-10 to include course content and stick strategies |  | 2016-11-29 |  |  | Check in with customers to see how they're doing
3-Delivery | Content | Opt In List (minus Customers) and people who went through the 7-day trial and didn't purchase - send people to downsell campaign |  | 2016-12-08
3-Delivery | Admin | Set up survey to gather testimonials |  | 2016-12-16
3-Delivery | Admin | Update procedures based on lessons learned and analyltics |  | 2016-12-16 |  |  | End of program
3-Delivery | Technical | Customer List - send them to upsell campaign |  | 2016-12-16 |  |  | End of program
3-Delivery | Technical | Add new testimonials to sales page |  | 2016-12-28 |  |  | Get testimonials from survey
AFFILIATES
| Admin | Pay affiliates after refund period |  | 2017-01-27 |  |  | 60 Days after Purchase?